## Slide 1: Revised Asia Welcome Call Guidelines – Market Gap Assessment
 |  |  | 100% Coverage: |  |  | 30% Coverage: | Dist L1B Escalation and Review of Response and Unreachables
 |  |  | Vulnerable Customers | High Risk Products | FNA/RPQ Mismatch | Medium Risk Product | 
HK |  |  | ü | Gap for UL | Gap for FNA Mismatch | Gap | Gap
SG | Agency |  | ü | ü | ü | Gap | Gap
 | Banca & Brokerage |  | Welcome Call Exemption Requested for Banca and Brokerage Channel (Pre-transaction calls performed following regulatory requirements for vulnerable customers, ILP, etc.) |  |  |  | 
JP | PA & IA |  | ü | ü | Gap | ü | Gap
 | FI |  | Welcome Call Exemption Requested for FI Channel (Currently welcome calls are conducted for 1 bank and 2 security firms) |  |  |  | 
CN |  |  | ü | ü | ü | ü | ü
VN |  |  | With PIVC adoption, full compliance with Guidelines |  |  |  | 
ID |  |  | ü | ü | Gap | ü | ü
PH |  |  | Gap (CAP already created to address gaps) | ü | Gap (CAP already created to address gaps) | ü | ü
MY |  | Agency | ü | Gap | Gap | ü | Gap
 |  | Banca | ü | Generally ü (UL with premium below RM10,000 are excluded) | Gap | ü | Gap
KH |  |  | ü | ü | ü | ü | ü (SOP already updated to address gaps)
MM |  |  | ü | ü | ü | ü | ü (SOP already updated to address gaps)
1

## Slide 2
Coverage for High & Medium Risk Products
HK Status
2
Local working group level exploring expanding use of letters
Local Leadership view that achieving regulatory requirements already sufficient
Local working group to discuss with Leaders to align
Potential deviation request
FNA/RPQ Mismatch

## Slide 3
Coverage for Medium Risk Products
SG Banca & Brokerage Channel
SG Status
3
Exploring email communications
To work with SG on plan-for-plan CAP re above
SG requested roadmap target date: End of Aug 2026

## Slide 4
JP FI
Channel
JP Status
4
JP is reaching out to banks for feedback
Call set up with JP on Fri to discuss findings
JP already has CAP on flagging FNA/RPQ mismatches
Potential deviation request required for FI channel
FNA/RPQ Mismatch

## Slide 5
MY Status
5
Working group explored using email communications (short-term) and digital platform (long-term) to address gap
Yet to algin with Local Leadership who may have different views
Need to set up system to flag FNA/RPQ mismatches
Potential deviation request required
FNA/RPQ Mismatch
Coverage for High Risk Products

## Slide 6
Dist. L1B Review and Escalation
6
Unreachable Calls Protocol: Escalate to local Dist. Line 1B within 7 business days.
Indications of Potential Mis-selling: Escalate to local Dist. L1B and Compliance within 1 day.
Dist. L1B Review: Markets Dist. L1B review will focus on policy legitimacy, potential distribution quality issues, and indications of misconduct or fraud. Suspected misconduct may be escalated to local Compliance immediately for investigation.
Reference: Revised Asia Welcome Call Guidelines:
Dist. L1B Review: To review